## Sheet1
2023-09-01 |  |  |  | 2023-10-01 |  |  |  | 2023-11-01 |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01 |  |  |  | 2024-05-01 |  |  |  | 2024-06-01 |  |  |  | 2024-07-01 |  |  |  | 2024-08-01
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48
Initial project idea | [15 empty] | First stage of testing | [15 empty] | Login screen interface
| Research into similar systems | [31 empty] | Login system and accounts
[17 empty] | Main menu | [16 empty] | Connect accounts to database
|  | Client interview | [15 empty] | Level selection screen | [17 empty] | Design and create 12 levels increasing in difficulty
|  | Determine objectives | [17 empty] | Game over screen
|  |  | Propose solution | [16 empty] | Level completion screen | [17 empty] | Add boss levels
|  |  | Analyse limitations | [16 empty] | Pause screen | [19 empty] | Second stage of testing
|  |  |  | Interface/ graphics designs | [16 empty] | Instruction screen
[6 empty] | Pseudocode algorithms | [15 empty] | Level analysis and graphs | [18 empty] | Test table
[8 empty] | Hierarchy Chart | [32 empty] | Compile test videos
[8 empty] | Class Tables | [13 empty] | Graph screen | [19 empty] | Outline issues and errors
[8 empty] | Data Structures table | [14 empty] | Main shop menu
[9 empty] | Basic game framework | [13 empty] | Skill tree interface | [19 empty] | Evaluate against objectives
[9 empty] | Player movement | [15 empty] | Implement skills into main game
[9 empty] | Player animations | [34 empty] | Undertake client & user feedback
[10 empty] | Player shooting/bullets | [16 empty] | Skin selection interface
[11 empty] | Enemy movement | [15 empty] | Skin selection / purchasing | [16 empty] | Analyse feedback
[11 empty] | Enemy animations | [17 empty] | Set up database | [15 empty] | Make necessary changes
[12 empty] | Player and enemy interactions | [17 empty] | Connect completed levels to database
[30 empty] | Connect purchased skins to database | [15 empty] | Potential extensions and improvements
[13 empty] | Collectables framework | [16 empty] | Connect purchased skills to database
Connect level/enemy information to database
[13 empty] | Coin collectable | [33 empty] | Final conclusion
Scrap collectable
Nuke collectable
Health collectable
Player level up system